## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 |  | 2026-07-02 | The code submission workflow did not consistently reject malformed Python source before the analysis pipeline, causing invalid syntax to reach downstream processing. | Sprint 1 | Veer | Logical | Separated syntax validation from the analysis workflow and corrected invalid-source handling before review execution. | 2026-07-03 | Closed | Retested with invalid Python source.
2 |  | 2026-07-04 | Uploaded Python and Java source files were not handled consistently because language-specific file handling was not fully aligned with the submission workflow. | Sprint 1 | Veer | Logical | Updated source-file handling so Python and Java uploads retain the detected language and source content correctly. | 2026-07-05 | Closed | Verified with Python and Java source files.
3 |  | 2026-07-05 | Knowledge-base preparation required more consistent document chunking and indexing so secure-coding material could be retrieved as usable context. | Sprint 1 | Veer | Maintainability | Refined document processing and indexing configuration for the secure-coding knowledge base. | 2026-07-06 | Closed | Validated indexed knowledge-base content.
4 |  | 2026-07-08 | The initial code-analysis output did not consistently distinguish code-quality findings from security findings in the unified review result. | Sprint 2 | Veer | Logical | Standardized finding fields during orchestration and preserved the originating analysis category. | 2026-07-09 | Closed | Verified merged findings structure.
5 |  | 2026-07-10 | Security findings could receive inconsistent severity labels when different detection rules produced similar vulnerability categories. | Sprint 2 | Veer | Logical | Normalized severity handling in the security-analysis output and aligned classifications with the existing severity scheme. | 2026-07-11 | Closed | Validated against known vulnerability samples.
6 |  | 2026-07-14 | The concurrent analysis pipeline could produce incomplete downstream results when one analysis agent raised an exception. | Sprint 3 | Veer | Logical | Added safe agent execution and failure handling so the orchestration pipeline records agent status without terminating the complete review. | 2026-07-15 | Closed | Verified multi-agent execution flow.
7 |  | 2026-07-16 | Merged findings did not consistently preserve the source location information needed for actionable vulnerability display. | Sprint 3 | Veer | Logical | Updated finding aggregation to retain line and source-context information where provided by analysis agents. | 2026-07-17 | Closed | Verified location-aware findings.
8 |  | 2026-07-17 | Python and Java review behavior was not initially consistent because language-specific validation and analysis paths were not fully separated. | Sprint 3 | Veer | Logical | Separated language-aware validation and review handling so Java source is not passed through Python-specific parsing. | 2026-07-18 | Closed | Verified with Python and Java samples.
9 |  | 2026-07-20 | A remediation result could become too generic when the finding did not provide enough source context for a specific recommendation. | Sprint 4 | Veer | Maintainability | Passed submitted source-code context into remediation generation and improved finding enrichment before remediation. | 2026-07-21 | Closed | Verified contextual remediation output.
10 |  | 2026-07-22 | The remediation output did not consistently preserve the exact offending source line required for a direct developer fix. | Sprint 4 | Veer | Logical | Added source-line and surrounding-line context to remediation inputs and updated the remediation response structure. | 2026-07-23 | Closed | Verified against source-backed findings.
11 |  | 2026-07-26 | The PR summary did not always present severity counts and review status in a consistent structure after findings were merged. | Sprint 5 | Veer | Logical | Standardized PR summary input metrics while preserving the existing scoring calculations. | 2026-07-27 | Closed | Verified severity breakdown in review output.
12 |  | 2026-07-29 | Finding details were difficult to act on when problem explanation and remediation guidance were presented without a clear developer-oriented structure. | Sprint 5 | Veer | User Interface | Reorganized finding presentation into problem, impact, change recommendation, corrected code, best practice, and references sections. | 2026-07-30 | Closed | Verified improved findings readability.
13 |  | 2026-08-01 | Conversational assistant responses could become generic when the active finding and submitted source code were not fully included in the assistant context. | Sprint 6 | Veer | Logical | Forwarded source code, findings, remediations, scores, and PR summary context to the conversational assistant. | 2026-08-02 | Closed | Validated context-aware assistant responses.
14 |  | 2026-08-04 | RAG responses could retrieve overlapping secure-coding passages, reducing clarity and making assistant answers unnecessarily repetitive. | Sprint 6 | Veer | Maintainability | Improved retrieval handling and context preparation to reduce duplicate knowledge-base content before LLM generation. | 2026-08-05 | Closed | Verified with security and secure-coding questions.
15 |  | 2026-08-06 | The exported PDF report did not initially provide a sufficiently concise executive view of findings, severity, remediation, and code-health information. | Sprint 7 | Veer | User Interface | Refined the report layout into a professional single-page executive format while retaining required review information. | 2026-08-08 | Closed | Verified final report presentation.
16 |  | 2026-08-09 | Exported review information could become inconsistent when findings, remediation details, and summary information were assembled from different pipeline outputs. | Sprint 7 | Veer | Logical | Aligned report generation inputs with the unified findings, remediation, and PR summary results. | 2026-08-10 | Closed | Verified during end-to-end report generation.
17 |  | 2026-08-11 | End-to-end testing exposed cases where syntax validation, language detection, and full AI review could be triggered as overlapping operations. | Sprint 8 | Veer | Logical | Separated syntax validation from full AI review execution and corrected the language-aware validation flow. | 2026-08-12 | Closed | Verified Python and Java validation flow.
18 |  | 2026-08-13 | Conversational assistant output could contain overly technical or incomplete explanations that reduced usefulness for junior developers and mentors. | Sprint 8 | Veer | Standards | Refined assistant response instructions to prioritize simple explanations, direct changes, and source-grounded remediation guidance. | 2026-08-14 | Closed | Validated conversational response clarity.
19 |  | 2026-08-14 | Final documentation and demonstration material required consistency between documented capabilities, test scenarios, reports, and implemented project modules. | Sprint 8 | Veer | Standards | Cross-checked final documentation and demonstration content against the implemented project modules and milestone scope. | 2026-08-15 | Closed | Verified during final documentation review.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others