## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | As a developer, I want to understand OWASP vulnerabilities and secure coding practices, so that the review rules are based on recognized standards. | Must Have | Project scope | Veer | Completed
1 | 1 | US-02 | As a project team, I want to study code-smell patterns and RAG architecture, so that the analysis platform has a clear technical foundation. | Must Have | US-01 | Veer | Completed
1 | 2 | US-03 | As a project team, I want to design the multi-agent architecture and agent responsibilities, so that analysis responsibilities are clearly separated. | Must Have | US-01, US-02 | Veer | Completed
1 | 2 | US-04 | As a developer, I want defined orchestration flow and data models, so that agent outputs can be combined consistently. | Must Have | US-03 | Veer | Completed | s
1 | 2 | US-05 | As a developer, I want to submit Python or Java code by paste or file upload, so that the platform can review source code. | Must Have | US-03 | Veer | Completed
2 | 2 | US-06 | As a developer, I want syntax validation for submitted Python and Java code, so that invalid source is identified before analysis. | Must Have | US-05 | Veer | Completed
2 | 2 | US-07 | As a project team, I want a secure coding knowledge base indexed with chunking and embeddings, so that RAG can retrieve relevant guidance. | Must Have | US-01, US-02 | Veer | Completed
2 | 2 | US-08 | As a developer, I want vector-store indexing of secure coding documents, so that the assistant can retrieve relevant standards. | Must Have | US-07 | Veer | Completed
3 | 3 | US-09 | As a developer, I want code smells and complexity issues detected with severity scoring, so that maintainability problems are easy to prioritize. | Must Have | US-05, US-06 | Veer | Completed
3 | 3 | US-10 | As a security reviewer, I want OWASP-standard vulnerabilities detected and classified by severity and location, so that security risks are actionable. | Must Have | US-05, US-07 | Veer | Completed
3 | 3 | US-11 | As a project team, I want Code Analysis and Security agents to run in parallel, so that review execution is efficient. | Must Have | US-09, US-10 | Veer | Completed
4 | 4 | US-12 | As a developer, I want findings from all analysis agents merged into one list, so that I can review issues in one place. | Must Have | US-11 | Veer | Completed
4 | 4 | US-13 | As a project team, I want known Python and Java samples with expected issues, so that detection accuracy can be validated. | Should Have | US-09, US-10 | Veer | Completed
4 | 4 | US-14 | As a reviewer, I want location-specific findings with consistent severity labels, so that I can verify detected issues quickly. | Must Have | US-12, US-13 | Veer | Completed
5 | 5 | US-15 | As a developer, I want specific remediation recommendations, so that I know exactly how to fix each finding. | Must Have | US-12, US-14 | Veer | Completed
5 | 5 | US-16 | As a developer, I want corrected code examples and best-practice explanations, so that I can apply secure fixes confidently. | Must Have | US-15 | Veer | Completed
5 | 5 | US-17 | As a reviewer, I want an executive PR summary with severity breakdown and prioritized fixes, so that review decisions are quick and clear. | Must Have | US-12, US-15 | Veer | Completed
6 | 6 | US-18 | As a developer, I want a findings display with severity, remediation, and code-health scoring, so that review quality is visible at a glance. | Must Have | US-14, US-15 | Veer | Completed
6 | 6 | US-19 | As a developer, I want a conversational RAG assistant for follow-up questions, so that I can understand vulnerabilities and secure coding guidance. | Must Have | US-08, US-12 | Veer | Completed
6 | 6 | US-20 | As a developer, I want assistant responses grounded in retrieved secure-coding knowledge, so that guidance is relevant to the project domain. | Must Have | US-19 | Veer | Completed
7 | 7 | US-21 | As a reviewer, I want an exportable PDF code-review report, so that review results can be shared professionally. | Must Have | US-17, US-18 | Veer | Completed
7 | 7 | US-22 | As a reviewer, I want findings summary, severity breakdown, remediation roadmap, and code-quality assessment in the report, so that the report is decision-ready. | Must Have | US-21 | Veer | Completed
7 | 7 | US-23 | As a project team, I want end-to-end tests across varied Python and Java samples, so that the integrated pipeline is validated. | Must Have | US-13, US-17, US-19, US-21 | Veer | Completed
8 | 8 | US-24 | As a project team, I want agent prompts and severity scoring optimized, so that analysis results are consistent and understandable. | Should Have | US-23 | Veer | Completed
8 | 8 | US-25 | As a project team, I want RAG retrieval and conversational accuracy validated, so that assistant responses remain relevant and grounded. | Must Have | US-20, US-23 | Veer | Completed
8 | 8 | US-26 | As a project team, I want technical documentation and project-report content prepared, so that the final implementation is professionally documented. | Must Have | US-21, US-23 | Veer | Completed
8 | 8 | US-27 | As a project team, I want a final demonstration using at least three distinct code samples, so that the completed platform can be evaluated across varying complexity. | Must Have | US-23, US-24, US-25 | Veer | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 307 | 23.3 | 28.8 | 28.3 | 28.2 | 26.2 | 28.4 | 22.7 | 25.2 | 24.2 | 18.7 | 20.2 | 14.5 | 13 | 6
SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
US-01 | T1-1 | Study OWASP vulnerability standards and secure coding guidelines | 2026-07-01 | 2026-07-01 | Veer | Research | Completed | 4 | Day 1: 2; Day 2: 2
US-02 | T1-2 | Study code-smell patterns and RAG architecture | 2026-07-01 | 2026-07-02 | Veer | Research | Completed | 4 | Day 1: 2; Day 2: 2
US-03 | T1-3 | Design multi-agent system architecture | 2026-07-02 | 2026-07-03 | Veer | Design | Completed | 6 | Day 2: 3; Day 3: 3
US-03 | T1-4 | Define agent responsibilities and boundaries | 2026-07-03 | 2026-07-03 | Veer | Design | Completed | 4 | Day 3: 2; Day 4: 2
US-04 | T1-5 | Design orchestration flow and data models | 2026-07-04 | 2026-07-04 | Veer | Design | Completed | 5 | Day 4: 2.5; Day 5: 2.5
US-05 | T1-6 | Implement direct code submission | 2026-07-04 | 2026-07-05 | Veer | Development | Completed | 6 | Day 5: 3; Day 6: 3
US-05 | T1-7 | Implement Python/Java file upload handling | 2026-07-05 | 2026-07-06 | Veer | Development | Completed | 6 | Day 6: 3; Day 7: 3
US-06 | T1-8 | Implement syntax validation for supported languages | 2026-07-06 | 2026-07-06 | Veer | Development | Completed | 5 | Day 7: 2.5; Day 8: 2.5
SPRINT 2 BACKLOG
US-07 | T2-1 | Collect and prepare secure coding knowledge documents | 2026-07-07 | 2026-07-07 | 3- Completed | Knowledge Base | Completed | 5 | Day 1: 2.5; Day 2: 2.5
US-07 | T2-2 | Implement document chunking | 2026-07-07 | 2026-07-08 | 3- Completed | Development | Completed | 5 | Day 2: 2.5; Day 3: 2.5
US-07 | T2-3 | Generate embeddings for indexed content | 2026-07-08 | 2026-07-09 | 3- Completed | Development | Completed | 5 | Day 3: 2.5; Day 4: 2.5
US-08 | T2-4 | Configure vector-store indexing | 2026-07-09 | 2026-07-10 | 3- Completed | Development | Completed | 6 | Day 4: 3; Day 5: 3
US-08 | T2-5 | Validate indexed knowledge retrieval | 2026-07-10 | 2026-07-11 | 3- Completed | Testing | Completed | 4 | Day 6: 2; Day 7: 2
US-06 | T2-6 | Validate Python and Java syntax-validation paths | 2026-07-11 | 2026-07-12 | 3- Completed | Testing | Completed | 4 | Day 8: 2; Day 9: 2
US-05 | T2-7 | Integrate submission flow with analysis entry point | 2026-07-12 | 2026-07-12 | 3- Completed | Integration | Completed | 5 | Day 10: 2.5; Day 11: 2.5
SPRINT 3 BACKLOG
US-09 | T3-1 | Implement code-smell and complexity detection | 2026-07-13 | 2026-07-13 | Veer | Development | Completed | 8 | Day 1: 2.7; Day 2: 2.7; Day 3: 2.7
US-09 | T3-2 | Implement code-quality severity scoring | 2026-07-13 | 2026-07-14 | Veer | Development | Completed | 5 | Day 3: 2.5; Day 4: 2.5
US-10 | T3-3 | Implement OWASP vulnerability detection | 2026-07-14 | 2026-07-15 | Veer | Development | Completed | 8 | Day 4: 2.7; Day 5: 2.7; Day 6: 2.7
US-10 | T3-4 | Implement vulnerability severity classification | 2026-07-15 | 2026-07-16 | Veer | Development | Completed | 5 | Day 6: 2.5; Day 7: 2.5
US-10 | T3-5 | Implement location-specific finding flagging | 2026-07-16 | 2026-07-17 | Veer | Development | Completed | 4 | Day 8: 2; Day 9: 2
US-09 | T3-6 | Test code-quality findings on sample code | 2026-07-17 | 2026-07-18 | Veer | Testing | Completed | 4 | Day 10: 2; Day 11: 2
US-10 | T3-7 | Test security findings on known vulnerable samples | 2026-07-18 | 2026-07-18 | Veer | Testing | Completed | 5 | Day 12: 2.5; Day 13: 2.5
SPRINT 4 BACKLOG
US-11 | T4-1 | Implement parallel Code Analysis and Security execution | 2026-07-19 | 2026-07-19 | Veer | Integration | Completed | 6 | Day 1: 3; Day 2: 3
US-12 | T4-2 | Merge analysis outputs into unified findings | 2026-07-19 | 2026-07-20 | Veer | Integration | Completed | 5 | Day 3: 2.5; Day 4: 2.5
US-14 | T4-3 | Normalize finding location and severity fields | 2026-07-20 | 2026-07-21 | Veer | Development | Completed | 4 | Day 5: 2; Day 6: 2
US-13 | T4-4 | Prepare known Python validation samples | 2026-07-21 | 2026-07-22 | Veer | Testing | Completed | 4 | Day 7: 2; Day 8: 2
US-13 | T4-5 | Prepare known Java validation samples | 2026-07-22 | 2026-07-23 | Veer | Testing | Completed | 4 | Day 8: 2; Day 9: 2
US-14 | T4-6 | Validate detection accuracy and location mapping | 2026-07-23 | 2026-07-24 | Veer | Testing | Completed | 6 | Day 10: 3; Day 11: 3
US-12 | T4-7 | Validate end-to-end findings pipeline | 2026-07-24 | 2026-07-24 | Veer | Testing | Completed | 5 | Day 12: 2.5; Day 13: 2.5
SPRINT 5 BACKLOG
US-15 | T5-1 | Implement Remediation Agent | 2026-07-25 | 2026-07-25 | Veer | Development | Completed | 8 | Day 1: 2.7; Day 2: 2.7; Day 3: 2.7
US-16 | T5-2 | Generate corrected code examples | 2026-07-25 | 2026-07-26 | Veer | Development | Completed | 6 | Day 4: 3; Day 5: 3
US-16 | T5-3 | Generate best-practice explanations | 2026-07-26 | 2026-07-27 | Veer | Development | Completed | 4 | Day 5: 2; Day 6: 2
US-17 | T5-4 | Implement PR Summary Agent | 2026-07-27 | 2026-07-28 | Veer | Development | Completed | 8 | Day 6: 2.7; Day 7: 2.7; Day 8: 2.7
US-17 | T5-5 | Generate severity breakdown and prioritized fixes | 2026-07-28 | 2026-07-29 | Veer | Development | Completed | 5 | Day 8: 2.5; Day 9: 2.5
US-15 | T5-6 | Validate remediation against findings | 2026-07-29 | 2026-07-30 | Veer | Testing | Completed | 5 | Day 10: 2.5; Day 11: 2.5
US-17 | T5-7 | Validate PR summary output | 2026-07-30 | 2026-07-30 | Veer | Testing | Completed | 4 | Day 12: 2; Day 13: 2
SPRINT 6 BACKLOG
US-18 | T6-1 | Implement findings display module | 2026-07-31 | 2026-07-31 | Veer | Frontend | Completed | 8 | Day 1: 2.7; Day 2: 2.7; Day 3: 2.7
US-18 | T6-2 | Display severity and code-health scores | 2026-07-31 | 2026-08-01 | Veer | Frontend | Completed | 5 | Day 4: 2.5; Day 5: 2.5
US-18 | T6-3 | Display per-finding remediation and code context | 2026-08-01 | 2026-08-02 | Veer | Frontend | Completed | 6 | Day 6: 3; Day 7: 3
US-19 | T6-4 | Implement conversational RAG assistant interface | 2026-08-02 | 2026-08-03 | Veer | Development | Completed | 8 | Day 8: 4; Day 9: 4
US-20 | T6-5 | Connect assistant to retrieved knowledge context | 2026-08-03 | 2026-08-04 | Veer | Integration | Completed | 6 | Day 9: 3; Day 10: 3
US-19 | T6-6 | Validate follow-up vulnerability questions | 2026-08-04 | 2026-08-05 | Veer | Testing | Completed | 5 | Day 11: 2.5; Day 12: 2.5
US-20 | T6-7 | Validate grounded assistant responses | 2026-08-05 | 2026-08-05 | Veer | Testing | Completed | 4 | Day 13: 2; Day 14: 2
SPRINT 7 BACKLOG
US-21 | T7-1 | Implement exportable PDF report generation | 2026-08-06 | 2026-08-06 | Veer | Development | Completed | 8 | Day 1: 2.7; Day 2: 2.7; Day 3: 2.7
US-22 | T7-2 | Add findings summary and severity breakdown to report | 2026-08-06 | 2026-08-07 | Veer | Development | Completed | 5 | Day 4: 2.5; Day 5: 2.5
US-22 | T7-3 | Add remediation roadmap and code-quality assessment | 2026-08-07 | 2026-08-08 | Veer | Development | Completed | 5 | Day 6: 2.5; Day 7: 2.5
US-23 | T7-4 | Run integrated Python code-review test flow | 2026-08-08 | 2026-08-08 | Veer | Testing | Completed | 6 | Day 8: 3; Day 9: 3
US-23 | T7-5 | Run integrated Java code-review test flow | 2026-08-08 | 2026-08-09 | Veer | Testing | Completed | 6 | Day 9: 3; Day 10: 3
US-21 | T7-6 | Validate PDF report completeness | 2026-08-09 | 2026-08-10 | Veer | Testing | Completed | 4 | Day 11: 2; Day 12: 2
US-23 | T7-7 | Record end-to-end test observations | 2026-08-10 | 2026-08-10 | Veer | Testing | Completed | 4 | Day 13: 2; Day 14: 2
SPRINT 8 BACKLOG
US-24 | T8-1 | Optimize agent prompts for clear and consistent outputs | 2026-08-11 | 2026-08-11 | Veer | Optimization | Completed | 6 | Day 1: 3; Day 2: 3
US-24 | T8-2 | Validate severity scoring consistency | 2026-08-11 | 2026-08-12 | Veer | Optimization | Completed | 5 | Day 3: 2.5; Day 4: 2.5
US-25 | T8-3 | Optimize and validate RAG retrieval relevance | 2026-08-12 | 2026-08-13 | Veer | Optimization | Completed | 6 | Day 5: 3; Day 6: 3
US-25 | T8-4 | Validate conversational assistant accuracy | 2026-08-13 | 2026-08-13 | Veer | Testing | Completed | 5 | Day 7: 2.5; Day 8: 2.5
US-26 | T8-5 | Prepare technical documentation and project report | 2026-08-13 | 2026-08-14 | Veer | Documentation | Completed | 8 | Day 9: 2.7; Day 10: 2.7; Day 11: 2.7
US-27 | T8-6 | Prepare three-code-sample final demonstration | 2026-08-14 | 2026-08-15 | Veer | Demonstration | Completed | 6 | Day 11: 3; Day 12: 3
US-26 | T8-7 | Final documentation and demonstration review | 2026-08-15 | 2026-08-15 | Veer | Validation | Completed | 4 | Day 13: 2; Day 14: 2
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 14 | No major blockers. | Proceed with architecture and submission implementation.
Sprint 2 | Day 14 | Knowledge-base indexing required validation before use. | Validate retrieval before dependent assistant work.
Sprint 3 | Day 14 | Agent rule tuning required during implementation. | Tune detection and severity rules using known samples.
Sprint 4 | Day 14 | Integration validation was required after parallel execution. | Run integrated findings validation.
Sprint 5 | Day 14 | Prompt/output consistency required refinement. | Refine remediation and PR-summary outputs.
Sprint 6 | Day 14 | Assistant context and retrieval relevance required validation. | Validate grounded assistant responses and findings display.
Sprint 7 | Day 14 | Report layout and completeness required final checks. | Finalize report generation and end-to-end tests.
Sprint 8 | Day 14 | Final validation and documentation review required coordination. | Complete optimization, documentation, and final demonstration review.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-07-01 | 2026-07-06 | Veer Bachhawat | Established OWASP/RAG foundation and project architecture. | Avoid broad scope expansion during foundation work. | Keep architecture and requirements traceable to milestones. | Maintain milestone-linked planning.
2 | 2 | 2026-07-07 | 2026-07-12 | Veer Bachhawat | Submission flow, syntax validation, and knowledge indexing were structured. | Avoid delaying retrieval validation until assistant implementation. | Validate knowledge indexing as soon as it is available. | Add retrieval validation to integration planning.
3 | 3 | 2026-07-13 | 2026-07-18 | Veer Bachhawat | Code and security analysis agents were implemented with severity scoring. | Avoid inconsistent severity interpretations across detectors. | Keep findings location-specific and actionable. | Standardize severity rules.
4 | 4 | 2026-07-19 | 2026-07-24 | Veer Bachhawat | Parallel orchestration and unified findings improved the review pipeline. | Avoid integration work without representative samples. | Use known Python and Java samples for validation. | Maintain cross-agent integration tests.
5 | 5 | 2026-07-25 | 2026-07-30 | Veer Bachhawat | Remediation and PR-summary outputs became actionable review artifacts. | Avoid generic remediation language. | Prefer exact finding context and corrected examples. | Continue prompt refinement.
6 | 6 | 2026-07-31 | 2026-08-05 | Veer Bachhawat | Findings display and RAG conversational assistance were integrated. | Avoid answers that are not grounded in retrieved project knowledge. | Keep assistant responses clear and developer-focused. | Validate retrieval relevance and assistant accuracy.
7 | 7 | 2026-08-06 | 2026-08-10 | Veer Bachhawat | Report generation and end-to-end testing were completed. | Avoid overly long reports when an executive report is sufficient. | Keep reports concise, structured, and decision-ready. | Refine report layout and completeness checks.
8 | 8 | 2026-08-11 | 2026-08-15 | Veer Bachhawat | Prompt optimization, documentation, and final demonstration were prepared. | Avoid unsupported claims or undocumented project behavior. | Keep final evidence aligned with the implemented system. | Perform final consistency review before submission.